Customer Service Workshop

For XXXXXXXXXX

Project Plan

Created by Mark M. Tamer

MGTPerformance Improvement

Created January 12, 200X

Version 1.0

# Project Justification

## Business Needs  (Why do it?)

MGT has identified Client’s explicit need for a workshop to improve the performance of technical customer service representatives

Client’s will provide better customer service to their clients

## Feasibility  (What makes us think we can do it?)

We have strong executive commitment

We have an adequate budget

We have the necessary time to develop the courseware

We have expertise in instructional design

We have client subject matter experts

We have desktop publishing and word processing capabilities

# Project Charter

Client, Inc. has indicated a need to improve the performance of their technical customer service representatives.  To meet this demand, we will develop a facilitator-led four hour Customer Service Workshop.

| Sponsor |  | Project Manager |  |
| --- | --- | --- | --- |
| Date |  | Date |  |

# Project Scope Statement

MGT Performance Improvement will develop a highly interactive Customer Service Workshop containing tools, knowledge, and skills for technical customer service representatives at Structure, Inc.

This workshop will be four hours in length and will be instructor-led.  The course will be modularized for easy delivery.  Sound adult learning principles will be employed to facilitate the learning process.

Content will include:

Company Best Practices

Industry Best Practices

Common Pitfalls to Avoid

Boundary Management

Interpersonal Awareness

General Phone Skills

Vendor (3rd party) Management

Problem Solving

Using Questions to Uncover Problems

Identifying Explicit vs. Implied Problems

Deliverables will include:

Project Plan

Requirements Document

Design Document

Student Guide

Facilitator Guide

PowerPoint Slides

Job Aids (Paper)

Audio Tape

# Stakeholders

| Stakeholder | Role | Organization | Contact Info |
| --- | --- | --- | --- |
| Ben Sydner | Executive Sponsor | MGT | Phone: 303-693-8832 Fax: 303-727-6753 Email: brsnyder@sic-i.com |
| Don Crabtree | Program Director | MGT | Phone: 800-747-9783 Fax: 303-756-2211 Email: dcrabtree@MGT.com |
| Mark Tamer | Project Manager, Instructional Design | MGT Performance Improv. | Phone: 480-699-9393 Fax: 480-699-9393 Email: mtamer@mgtperformance.com |
| Joe Trey | Desktop Publishing | MGT | Phone: 800-747-9783 Fax: 303-756-2211 Email: jtrey@MGT.com |
| Michael Kuehn | Director of Sales | MGT | Phone: 800-747-9783 Fax: 303-756-2211 Email: mhuehn@MGT.com |
| Stephanie Kuehn | Client | (i) Structure, Inc. | Phone: 720.888.6233 Fax: Email: Stephanie.Kuehn@i-structure.com |
| End-users | SMEs | TBD | Phone: Fax: Email: |

# Benefits

Increase MGT’s market share

Demonstrate MGT’s ability to create learning solutions for client implied and explicit needs

Improve the performance of customer service representatives

Establish effective communication skills for customer service representatives

# Assumptions

All resources will be made available per project plan

Non of the final deliverables will infringe upon any known copyrights

MGT will replicate and distribute the final deliverables

(i) Structure will provide SMEs to populate the custom content.

MGT will be responsible for instructional design and development of the course materials.

MGT will be responsible for setting client expectations, replicating all workshop materials, and coordinating the logistics of the pilot and all other workshops.

Stock graphics will be used to support written materials and presentation slides

(i) Structure will convert all paper job aids to Web-based

# Exclusions

MGT will not obtain copyrights to the final deliverables

There will be no custom graphics to support written materials

MGT will not provide web-based job aids

# Constraints

The project manager, project team, and SME’s will be dedicated to this project part-time

The project team is geographically dispersed

We have three months to complete this project

# Strategies

Identify client expectations of workshop objectives

Identify end-user knowledge and performance needs

Recruit client SMEs to populate the content

Use Stephanie Kuehn’s expertise to validate the content

Employ Mark’s expertise in instructional design to assure high-impact

Conduct a pilot workshop to identify final revisions

The Student and Facilitator Guides will be developed in MS Word

The workshop presentation slides will be developed in MS PowerPoint

Stock graphics will be used to support written materials and presentation slides

An audio tape will be created as a teaching tool

# Risk Assessment

| Risk | Elimination / Mitigation Strategy |
| --- | --- |
| Workshop does not meet client expectations | Conduct client needs assessments to identify workshop objectives, Stephanie’s knowledge of client needs |
| Infringement of copyrighted material | Populate content using primary sources of information, custom design all materials (excluding graphics) |
| Unable to recruit client SMEs | Offer incentives to compensate for effort |
| Not enough time for project | Revisit project deadlines weekly and make adjustments as necessary |

# Required Resources

## Human Resources

Client subject matter experts

Desktop publisher

Stephanie Kuehn

## Material Resources

TBD

## Other Resources

TBD

# Work Breakdown Structure

TBD

# Project Schedule

| Phase | Objectives | Deliverables | Deadline |
| --- | --- | --- | --- |
| Assess | Collect user input from clients, program directors, facilitators Survey existing literature Distribute and collect assessment instrument Synthesize data Define needs | Needs Assessment Survey instrument, paper and email Needs Assessment Report Requirements Document | 1/19/01 |
| Design | Select and organize workshop modules Create workshop outline Select learning strategies / activities Design PowerPoint slide Template Design Facilitator template Design Student Guide template | Design Document PowerPoint Slide template Facilitator Guide template Student Guide template | 1/26 |
| Develop | Populate workshop content Create Facilitator Guide Create Student Guide Create PowerPoint slides Create Job Aids Create audio tape | Facilitator Guide Student Guide PowerPoint slides Certification questions Job Aids Audio Tape | 2/16 |
| Implement | Organize pilot workshop Conduct pilot workshop | Pilot workshop | 2/23 |
| Evaluate | Solicit feedback from participants Determine and incorporate beneficial refinements | Workshop Feedback form Final versions of workshop materials | 3/2 |