Technology and Operations

Client Services

Integration Project

Project Definition Document

### Developed By: MGT Performance Improvement, LLC

January 10, 200X

Project Definition Document

Table of Contents

1.	Executive Summary	2

1.1.	Overview High Level Summary	2

2.	About this Document	2

2.1.	Purpose	2

2.2.	Organization of this Document	2

3.	Project Description	3

3.1.	Introduction	3

3.2.	Scope Statement	3

3.3.	Objectives	3

3.4.	Assumptions and Constraints	4

3.5.	Major Deliverables	5

4.	Milestones	5

5.	Risk	5

6.	Project Strategy	6

7.	Project Rollout Strategy	6

8.	Project Organization, Roles and Responsibilities	6

8.1.	Introduction	6

8.2.	Management, Client, Development, and Support Roles	7

9.	Quality Plan	7

9.1.	Defined Quality Assurance Checkpoints	7

9.2.	Methodology, Standards and Procedures to Be Followed	7

10.	Communication Plan	7

10.1.	Introduction	7

10.2.	Weekly Project Meetings with Minutes	8

10.3.	Meetings/Conference Calls - General	8

10.4.	Project Status Meetings	8

11.	Change Control Plan	9

12.	Training Plan	9

13.	Facilities Plan	9

13.1.	Equipment	9

13.2.	Security Access	9

13.3.	Central Project File	9

14.	Appendix A  	10

# Executive Summary

## Overview High Level Summary

SunTrust has entered into an agreement to purchase Crestar Banks, which was approved during December, 1998.  Crestar employees will become SunTrust employees in accordance with the terms of the contract that defines the affected Crestar employees Compensation and Benefits Programs.

In reviewing the technical network infrastructure of both SunTrust and Crestar Banks, it was identified that the Novell servers and NDS infrastructure were very similar in regard to standards, procedures, technical design and operational support.  Because of the close similarities, management requested that the NDS Engineering Teams in conjunction with Novell Consulting review the current infrastructures in more detail and to make a recommendation as to whether the banks should remain as two separate NDS trees or migrate into one “enterprise-wide” NDS corporate tree.

# About this Document

## Purpose

The purpose of this document is to provide all participants involved with this project with information for them to understand:

- The Scope of the Project

- The Objectives of the Project

- Assumptions and Constraints

- Risk Analysis

- Strategy

- Organizational Roles and Responsibilities

This document will serve as the basis for organizing and kicking off the project.  Participants will use this information to plan, coordinate, and implement their roles in the project.  The intent is to facilitate cooperation, understanding and effective communication between all participating organizations.

## Organization of this Document

Section 3 describes the project including scope, objectives, assumptions, and constraints.  Section 4 lists milestones at a minimum through the Requirements Phase.  Section 5 presents an analysis of the perceived risks of the project at this point.  Sections 6 and 7 describe the strategy for implementation and rollout of the project.  Section 8 describes the project organization, roles and responsibilities. Section 10 addresses project communication procedures.  Change control procedures are outlined in Section 11 Section 12 contains the Training plan. Section 13 contains the Facilities Plan.

The Risk Assessment Questionnaire is to be placed in Appendix A.

# Project Description

## Introduction

As a result of the review of current Crestar and SunTrust network architectures  it was recommended that for ease of administration, manageability and standardization, the Novell NDS infrastructure should be migrated into the SunTrust NDS tree.  The advantages of a single tree structure include single user login and authentication to a corporate wide NDS structure allowing access to all network resources without regard to physical location.  In addition, the single NDS tree presents an organized database of all network resources such as servers, volumes, printers and user accounts providing a single point of administration and consolidation of administrative resources.  A single NDS tree will provide centralized monitoring of the tree for proper operation and can provide automated deployment of new applications across the company.

As a preventative measure to saturating WAN links with SAP and RIP traffic, and avert slow response time NetWare/IP (NWIP) will be put in place between the Crestar and SunTrust network environments.  This will allow only changes of SAP and RIP to be communicated.  In addition, NWIP will be placed on segments identified with low bandwidth (less than 256K) or high utilization to avoid degradation or saturation.

## Scope Statement

- The only Crestar users impacted by this project are those currently accessing the network via Netware servers.

- Analysis of the current Crestar tree for the purposes of administration standardization and migration into the SunTrust tree.

- Evaluation of options for integration of Crestar into the SunTrust NDS tree.

- Identify slow links in the Crestar environment so that NWIP can be implemented.

- To implement NWIP in the Crestar environment to reduce SAP traffic.

- Extend the SunTrust tree master NDS infrastructure into the Crestar environment.

## Objectives

- To provide network synchronization to allow access between Crestar and SunTrust users.

- To ensure that critical information flows are maintained  and that applications such as mainframe connectivity and e-mail are not impacted during the implementation of a single tree.

- Ensure that sensitive data is secured during and after the implementation of a single tree.

- To ensure that timing of the NDS/NWIP project coincides with other dependent project schedules in support of Crestar to SunTrust conversion schedules.

- To leverage existing SunTrust licensing agreements for software products, to the extent possible within the allotted time frames, to take advantage of SunTrust volume pricing agreements.

- To develop a comprehensive project plan for the NDS/NWIP project and to control and monitor all tasks and issues related to executing the plan.

- To communicate with other STSC and Crestar Departments as well as the NDS/NWIP project team members from both Crestar and SunTrust regarding the progress of the various stages of the overall project.

- To ensure the stability and integrity of Y2K compliance for the Crestar and SunTrust environments.

- Provide stability of WAN connectivity by implementation of NWIP to reduce SAP traffic.

## Assumptions and Constraints

Assumptions:

- Hardware required to execute this project has been included in merger budgets.

- Sufficient resources to complete this project will be available as identified in the project plan.

- Crestar and SunTrust personnel will make up the project team for this project.

- A Y2K exception will be granted to migrate the Courthouse Road site (within Capital Region) as a pilot and headquarters during the Y2K “soft freeze” but prior to the Y2K “hard freeze” in October.

- Non-implementation activities will be scheduled during the “hard” Y2K freeze from October through January.

- Business units do not have any conflicts with or objections to scheduled implementation dates.

- Operational roles and responsibilities will be defined prior to the execution of the NDS/NWIP project.

- Core project team for the NDS/NWIP project will be dedicated full time.

- Top Secret Ids will have been converted to RACF Ids prior to implementation of  a single tree.

- Naming of Crestar objects and servers will meet SunTrust naming standards prior to the implementation of a single tree.

- NWIP infrastructure will be in place prior to the implementation of a single tree.

- Obsolete NDS objects will have been removed from the Crestar tree prior to implementation of a single tree.

- Master replicas for all partitions will have been moved to Crestar master NDS server prior to implementation of a single tree.

- Crestar departmental trees will be merged into a single Crestar NDS tree prior to implementation of a single tree.

Constraints:

- Timelines for the NDS/NWIP project are extremely aggressive.

- Y2K “hard” freeze will be closely follow the completion of the first two implementations.  This does not allow for any slippage in the timeline.

- The security project is dependent upon the NDS/NWIP project timeline.

## Major Deliverables

- NDS/NWIP project plan

- Weekly team meetings (conference call) with minutes

- Issues log

- Weekly Status Reports

- Monthly budget analysis and projections

- Installation of NWIP infrastructure

- Installation of NDS Infrastructure

- Lab Build, Testing and Conclusions

- Pilot Implementation and Test

- Implementation of a single SunTrust/Crestar tree.

# Milestones

| Milestone | Date Range |
| --- | --- |
| IPX by Exception |  |
| NDS Master Infrastructure |  |
| NWIP Infrastructure |  |
| NWIP Remote Server Installs |  |
| Free Play IPX |  |
| Lab – Testing and Certification |  |
| Pilot |  |
| Implementation |  |

# Risk

The Vision Risk Assessment resulted in a rating of ???? for this project.  It is, however, imperative that everyone realizes that, due to the dependencies on this project and the short timeframe to accomplish it, there is no room for slippage on project tasks.

Major Identified Risks:

- Resources required to complete project are in contention with Y2k priorities.

- Short timeframe to complete project tasks and implement large numbers of users.

- Dependence of other projects on NDS/NWIP project.

- There is a possibility that a Y2K exception will not be granted for this project to proceed during the “soft freeze” period.

- Impact of changes to large numbers of workstations will be significant and could severely impact  users’ ability to access their applications and data.

See Risk Assessment Document – Appendix

# Project Strategy

| Phase | Strategy | Timeframe |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 6 |  |  |
| 7 |  |  |
| 8 |  |  |
| 9 |  |  |
| 10 |  |  |
| 11 |  |  |
| 12 |  |  |
| 13 |  |  |

# Project Rollout Strategy

Upon completion of testing in a lab environment, a pilot site will be implemented.  This site (Capitol Region) has been selected based on its limited number of users.  A pilot roll out will allow the processes developed in a lab environment to be implemented and fine tuned in a production environment with a relatively small risk of negative impact.   The Headquarters Region was selected as the second implementation prior to the Y2K “hard” freeze.  This region has 800 users.

# Project Organization, Roles and Responsibilities

## Introduction

The purpose of this section is to communicate the roles and responsibilities of each member of this project team to all participants.  The project team responsible for the Crestar desktop image creation and implementation is comprised of both Crestar and SunTrust members.

## Management, Client, Development, and Support Roles

- Management roles:

Project Sponsor:		Mark Brett,  Sr. Vice President, SunTrust

Project Executive:		Teresa Strickland, Vice-President, SunTrust

Project Manager:		Susan Levy, SunTrust

Project Team Lead:		Diane Wightman, Vice-President, Crestar

- Development roles:

Netware Engineers:		Lynne Williamson, (Contractor)  SunTrust

David Chung, Crestar

Robert Staley, (Contractor) Crestar

Technical Admin. Asst.:	(to be determined)

Technical Writer:		(to be determined)

- Support roles:   Support planning is included as a task within the project plan. A general approach is expected to be :

Technology Support Center – First point of contact for users with escalation to others as needed (ex. Crestar LAN Operations and Engineering, Desktop Management, IS Team and SunTrust Production Services, Client Services, Training Coordinator and Audit Representative.)

# Quality Plan

## Defined Quality Assurance Checkpoints

Quality assurance points will be defined as project milestones from the work plan.

## Methodology, Standards and Procedures to Be Followed

The SunTrust Vision Methodology will be followed throughout this project.

# Communication Plan

## Introduction

Communication is imperative between the Crestar and SunTrust Project members as well as the .  All status reports and communications relative to critical path tasks will be distributed to both teams.  All issues that rely on other groups for resolution will be recorded on the issues log  and reported to those groups with a request for a resolution date.

## Weekly Project Meetings with Minutes

Project Status Reports will be prepared weekly due to the relatively short duration of this project and the criticality of many of the tasks.  Included in the Project Status report will be:

- Project Progress Statement .

- Activities/accomplishments for the reporting period.

- Completed tasks with actual dates of completion (since last report).

- Tasks to be completed in the near term with scheduled dates of completion.

- Issues

A description of the issue, origination date, owner, due date, current disposition, and description of action or resolution. Highlight any issues to be elevated to management and suggested resolution.  Any showstoppers should be communicated.  A notation describing any change to the project plan should be noted on the issues log.

## Meetings/Conference Calls - General

Meetings shall have a published agenda, duration, location, facilitator and scribe.  The agenda will include approval of the previous meeting minutes as an order of business.

Due to the relatively short duration of this project and the criticality of all tasks being completed on time, distribution of documentation to be discussed at the meeting will be published 1 day in advance to allow for advance preparation.

Participants will include those deemed to be necessary for specific issue resolution or decision-making.  It will be necessary for decision-makers to send a designated decision-maker to any meeting that he or she cannot attend and to which he or she has been notified of a critical issue in advance.

Minutes will be maintained for all meetings relative to the project.  Meeting minutes should be distributed within four business days after the meeting for review.   All issues will be added to the issues log.  All decisions will be captured and all action items will be documented and assigned with a date required for resolution.

## Project Status Meetings

Due to the aggressive timeline for this project and the criticality of the tasks to be completed, status meetings will be conducted once a week with conference calls between Susan Levy, Diane Wightman, Robert Staley, Lynne Williamson,  David Chung, the project Administrative Assistant,  and the project Technical Writer with other participants requested as necessary for issues resolution or information input.

(Administrative Assistant) will be responsible for archiving of all materials required in the central repository.

The agenda for status meetings will be standard and will include:

Review (if participants desire) and approval of prior week’s meeting minutes.

Review of current week’s agenda with opportunity to add discussion items,

Review of project plan activities with updates by team members of percentage completions.

Review of issues list items and additions/update of status and comments.

Documentation of action items originated during the meeting.

# Change Control Plan

Standard Vision Change Control Procedures will be used on this project.  Change control will be required for changes to the following:

- Scope of the project.

- Changes to the milestones for the project.

- Any significant change to costs over budget.

# Training Plan

Training plan development is included as project tasks in the project plan.

# Facilities Plan

Facilities planning is included as project tasks in the project plan.

## Equipment

All equipment requirements relative to this project have been included as project tasks in the project plan and all associated costs have been reflected in the project budget.

## Security Access

## Central Project File

Scott Hosonitz will be responsible for the maintenance of a central project file at the Atlanta Center 5th floor location.

# Appendix A